## COPR
Change Request
Change Order No: 2
Cust Job/Contract No |  |  | PLS Job No | Job Description
C6PPTLM200. |  |  | 2TF039- | L-592 China to Amelia
CO Description: |  | PLANNED OUTAGE DELAYED 15 DAYS RESULTING IN LOSS OF PRODUCTION FOR ASSIGNED CREW - CREW WAS ONLY ABLE TO PERFORM WORK AT A 50% PRODUCTION LEVEL HENCE 90 HOURS (75-ST AND 15-OT) CHARGED FOR EACH INDINVIDUAL CLASSIFICATION AFFECTED, EQUIPMENT CHARGED FOR 75 HOURS. ADDITIONALLY, SOME EQUIPMENT WAS IDLED (35 HOURS PER UNIT) TO REDUCE COST IMPACT OF DELAY.
Date Submitted: |  |  |  | Submitted By: |  | Hernandez, Edgar Agustin
Status: |  | Pending |  | Owner Rep: |  | Goff, Johnny L.
Job Location: OD CO - OUTAGE DELAY CHANGE ORDER
Unit # |  | Unit Description |  |  | Notes |  | CO QTY | Unit Price | Total
PD - PerDiem |  | PerDiem |  |  | 11 MEN FOR 15 DAYS * 50% PRODUCTION |  | 82.5 | 90 | 7425
ST - TRANS-TX/SUPERINTENDENT |  | ST - TRANS-TX/SUPERINTENDENT |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 75 | 119.7 | 8977.5
ST - TRANS-TX/GENERAL FOREMAN |  | ST - TRANS-TX/GENERAL FOREMAN |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 75 | 99.5 | 7462.5
ST - TRANS-TX/LINEMAN |  | ST - TRANS-TX/LINEMAN |  |  | 3 MEN 15 DAYS * 50% PRODUCTION |  | 225 | 60.8 | 13680
ST - TRANS-TX/HOT APPRENTICE |  | ST - TRANS-TX/HOT APPRENTICE |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 75 | 55.3 | 4147.5
ST - TRANS-TX/EQUIPMENT OPERATOR |  | ST - TRANS-TX/EQUIPMENT OPERATOR |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 75 | 64.5 | 4837.5
ST - TRANS-TX/GROUNDMAN |  | ST - TRANS-TX/GROUNDMAN |  |  | 4 MEN 15 DAYS * 50% PRODUCTION |  | 300 | 35 | 10500
MAT-RENT |  | MAT-RENTAL (PER MAT PER DAY) |  |  | 945 MAT DAYS |  | 945 | 4 | 3780
OT - TRANS-TX/SUPERINTENDENT |  | OT - TRANS-TX/SUPERINTENDENT |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 15 | 143.7 | 2155.5
OT - TRANS-TX/GENERAL FOREMAN |  | OT - TRANS-TX/GENERAL FOREMAN |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 15 | 119.4 | 1791
OT - TRANS-TX/LINEMAN |  | OT - TRANS-TX/LINEMAN |  |  | 3 MEN 15 DAYS * 50% PRODUCTION |  | 45 | 73 | 3285
OT - TRANS-TX/HOT APPRENTICE |  | OT - TRANS-TX/HOT APPRENTICE |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 15 | 66.4 | 996
OT - TRANS-TX/EQUIPMENT OPERATOR |  | OT - TRANS-TX/EQUIPMENT OPERATOR |  |  | 1 MAN 15 DAYS * 50% PRODUCTION |  | 15 | 77.4 | 1161
OT - TRANS-TX/GROUNDMAN |  | OT - TRANS-TX/GROUNDMAN |  |  | 4 MEN 15 DAYS * 50% PRODUCTION |  | 60 | 42 | 2520
1/2P |  | 1/2 TON TRUCK |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 13.2 | 990
1/2P |  | 1/2 TON TRUCK |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 13.2 | 462
3/4P |  | 3/4 TON TRUCK |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 14.4 | 1080
3/4P |  | 3/4 TON TRUCK |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 14.4 | 504
FORK |  | FORKLIFTS |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 12 | 420
FORK |  | FORKLIFTS |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 12 | 900
TELE |  | TELEHANDLER |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 18 | 630
TELE |  | TELEHANDLER |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 18 | 1350
BUCK55 |  | BUCKET ( TO 55') |  |  | 2 UNITS 15 DAYS * 50% PRODUCTION |  | 150 | 28.35 | 4252.5
BUCK55 |  | BUCKET ( TO 55') |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 70 | 28.35 | 1984.5
BUCK85 |  | BUCKET (>75' - TO 125') |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 65 | 2275
BUCK85 |  | BUCKET (>75' - TO 125') |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 65 | 4875
TRACBKCR |  | TRACK BUCKET 125' |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 168 | 12600
TRACBKCR |  | TRACK BUCKET 125' |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 168 | 5880
DOZE |  | DOZER -D6/7 |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 33.6 | 1176
DOZE |  | DOZER -D6/7 |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 33.6 | 2520
P45 |  | PULLER 4 & 5 DRUM ROPE |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 33.6 | 2520
P45 |  | PULLER 4 & 5 DRUM ROPE |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 33.6 | 1176
RSTA |  | REEL STANDS |  |  | 3 UNITS 15 DAYS * 50% PRODUCTION |  | 225 | 4.8 | 1080
RSTA |  | REEL STANDS |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 125 | 4.8 | 600
TENSION |  | TENSIONER |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 18 | 630
TENSION |  | TENSIONER |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 18 | 1350
TRCR3040 |  | TRACK CRANE 30-40 TON |  |  | EQUIPMENT STAND-BY B&McD REQUEST |  | 35 | 168 | 5880
TRCR3040 |  | TRACK CRANE 30-40 TON |  |  | 1 UNIT 15 DAYS * 50% PRODUCTION |  | 75 | 168 | 12600
Change Order 2 Total: | [8 empty] | 140453.5